## Overview
Overall Event Risk Assessment
Document prepared by:
Prepared on behalf of the Organizer:
Version Dated: | 2020-02-10
THIS DOCUMENT SUPERSEDES ALL PREVIOUS VERSIONS.
PLEASE CHECK THE DATE TO ENSURE YOU ARE WORKING FROM THE CORRECT DOCUMENT.
Introduction
This document is designed to assess the risk and describe the controls to be undertaken for the
Overall Event Risk Assessment
The responsible event organizer is | 0
It is their responsibility to carry out the control measures described in this document with exception of those responsibilities allotted to sub-contractors. Separate risk assessments for all hazardous elements will be produced by the individual sub-contractors introducing the hazard. The author has prepared this document based on the information provided at the time of writing. It relates directly to the safety of following persons:
Members of the production team and their sub-contractors.
Visitors attending the event
It is the responsibility of the organizer to ensure that an on-going assessment and update of working methods undertaken takes place throughout the event by individual supervisors of relevant departments. Any changes resulting in an escalation of the either the severity or probability rating of an identified hazard or the discovery of a new hazard are reported to the Production Director and or the Safety Advisor immediately.
For the purposes of this document, the following job titles shall be used:
Project Manager | Overall responsibility for the safe delivery of the event
Zone Manager | Coordination of technical contractors; and implementation of the production schedule. Monitoring operations.
Site Manager | Oversee site logistics and installation and operation of site infrastructure.
Health & Safety Manager | Monitors on site work safety and crowd safety during the event.

## Risk Matrix
Risk Matrix
PROBABILITY | SEVERITY
| Insignificant (1) | Minor (2) | Moderate (3) | Major (4) | Catastrophic (5)
Rare (1) | 1 | 2 | 3 | 4 | 5
Possible (2) | 2 | 4 | 6 | 8 | 10
Likely (3) | 3 | 6 | 9 | 12 | 15
Often (4) | 4 | 8 | 12 | 16 | 20
Frequent/Almost Certain (5) | 5 | 10 | 15 | 20 | 25
Risk Levels
15 - 25 | Extreme Risk | Absolutely Unacceptably High Activity or industry should not proceed in current form
8 - 12 | High Risk | Unacceptably High Activity or industry should be modified to include remedial planning and action and be subject to detailed HSE assessment
4 – 6 | Moderate Risk | Acceptable but must be managed at “As Low As Reasonably Practicable” (ALARP) Activity or industry can operate subject to management and / or modification
1 -3 | Low Risk | Acceptable without required further action No action required unless escalation of risk is possible

## Overall Risk Assessment
Overall Event Risk Assessment
Risk Identification and assessment | [5 empty] | Description of Control measures |  | Responsibility and residual risk
# | Step 1 | Step 2 | Step 3 |  |  |  |  | Step 4
| Hazard | Who might be at risk | Risk Rating |  |  | What are you already Doing (List all the Control measure already in place) | Control Measures What further action, if any, is necessary, if so what Action is to be taken by whom and by when? | Actions |  | Residual Risk
|  |  | Probability (P) | Severity (S) | Rating (P X S) |  |  | Action Whom | Action By When | Probability (P) | Severity (S) | Rating (P X S)
Site Security during Build and Breakdown
1 | Access to working area by non-accredited personnel or the visitors (including children) | Visitors and non-working personnel | 4 | 4 | 16 | Approval gained from client to use site for event activities under control of event organiser. All workers to report to production/security office and provide ID and in turn receive a workers pass. All vehicles are signed in and out by security control check | Site to be secured by means of fencing and barriers. Install signage to warn of hazards of construction activities. Security personnel in place to guard entrances to the site, conduct patrols and confirm all personnel onsite accredited. Access routes to be maintained as clear of obstruction at all times. | Operations Manager Safety Advisor | As per production schedule | 1 | 4 | 4
2 | Emergency vehicle access to hospital | Ambulance personnel, event staff, visitors | 3 | 4 | 12 | All access routes are kept clear at all times. Staff made aware during site induction. Vehicle movement on public roads leading to ambulance bay kept to a minimum. | Controlled by security. | Security and Safety Advisor | Constantly | 1 | 4 | 4
3 | Deliveries of materials, infrastructure items or production equipment
4 | Collision between Vehicles and Pedestrians | Event Staff and Visitors or non-event personnel | 3 | 4 | 12 | Site is secured by venue so as to prevent access by non-event or other working persons. (see also site security). Security to be in place to check for authorised access. Agreement with venue operators to permit deliveries to site. Consent gained to allow unimpeded access by authorised delivery vehicles in advance where possible. | Delivery drivers to be advised of timings and location of access points according to production schedule. Pedestrian access route separate to that used by vehicles as far as possible. Personnel to wear Hi-Viz vest to aid visibility at all time Onsite speed limit to be imposed. | Operations Manager Safety Advisor | Constantly | 1 | 4 | 4
5 | Manual Handling | Event staff | 2 | 3 | 6 | Staff trained and experienced in manual handling of equipment and materials. Materials palletised so far as reasonably practicable. All contractors to ensure that their staff are trained in dynamic lifting techniques and are supervised by their crew chief. | Mechanical aids such as trolleys, wheeled flight-cases, forklifts etc to be utilised. Deliveries to be made as close as possible to point of use. Staff to use appropriate PPE for manual handling tasks. Staff to make use of appropriate team lifting techniques where relevant. | Operations Manager Safety Advisor | As per production schedule | 1 | 3 | 3
6 | Mechanical Handling | Event staff | 3 | 4 | 12 | Staff trained in use of mechanical handling equipment. Equipment (including lifting accessories) to be provided, tested and examined as safe for use. Deliveries to be palletised for ease of mechanical handling where possible. Warning beacons and alarms fitted to equipment. | Machinery to be operated by authorised and licensed personnel only. Unloading/loading to be undertaken in secured site only. Banksmen to supervise movement of machinery by means of hand signals. Delivery drivers to be available to assist with unusual or difficult loads. Operator to conduct appropriate test and inspection of machinery and safety features. Keys to be kept safe in the hands of authorised operators whenever plant not in use. NOT to be left unattended in the vehicles. | Operations Manager Safety Advisor | As per production schedule | 1 | 4 | 4
7 | Use of Plant such as forklifts/cranes
8 | Failure of lifting equipment or accessories | Event Staff | 3 | 4 | 12 | Equipment sourced from reputable contractors to meet specification of event managers. Equipment to be certified as safe for use by contractor. All lifting operations undertaken by competent personnel. | Accessories including slings, chains etc. to be examined as free from defect prior to use. Equipment to be used only within the range of its designed capabilities. Forklifts only to be used on ground that has been confirmed as stable and not subject to sudden subsidence and or collapse. | Operations Manager Safety Advisor | As per production schedule | 1 | 4 | 4
9 | Falling Objects | Event Staff, visitors | 3 | 4 | 12 | Trained and competent operators or sub-contractors. | Loading and unloading areas to be restricted to personnel involved in lifting operations only. Working areas to be identified by signage and/or barriers as appropriate. Loads to be secured from instability and transported at as low a height as is practicably possible. Personnel to use appropriate PPE when working beneath moving loads. | Production Director Safety Advisor | As per production schedule | 1 | 4 | 4
10 | Work at Height
11 | Falls from Height | Event Staff and Visitors | 3 | 4 | 12 | Activities planned to reduce the need to work at height wherever possible. Trained and competent personnel employed to undertake work where risk of fall from height exists. Personnel provided information on areas of risk and required control measures. Additional control measures in place for roof access: Only qualified personnel with internationally recognised rigging certification such as NRC (UK) and IGVW (German Standard). Appropriate PPE such as 2 point harness with fall damper is worn in addition to safety shoes and hard hats with chin strap. Participation in a roof access safety induction. | Fixed scaffolds to be used to provide secure working areas where practical. Handrails and guardrails to be installed on all platforms where a risk of falling may exist. Incomplete structures or scaffolds to be signed and barrier in place as necessary. MEWP’s to be used by competent, licensed operators only. Ladders or other temporary access equipment to be available for short duration work at height operations. Platform to be used by persons other than construction crew shall have edges highlighted with contrasting colored tape. Personnel required to use appropriate fall prevention PPE where no other protective measures exist. | Production Director Safety Advisor | As per production schedule | 1 | 4 | 4
12 | Falling Objects | Event Staff, Visitors | 3 | 3 | 9 | Site induction to include information on ensuring all work at height is undertaken safely. Workers on roof to use tethered tools. | Loose tools or equipment to be secured effectively whilst working at height. Platforms used by others to have kick boards to stop any equipment falling from the platforms. | Safety Advisor | As per production schedule | 1 | 3 | 3
13 | Digging operations | Staff | 2 | 4 | 8 | Information on underground services is obtained from venue. A digging permit is issued before digging is allowed. Visual inspection and search of the work area and potential services in the surrounds. | Digging apparatus operated by competent licensed personnel. Work areas are cordoned off. Digs are marked on site plan. | Safety Advisor | As per production schedule | 1 | 4 | 4
14 | Use of generators and electrical power supplies
15 | Electric Shock | Event Staff and Visitors | 3 | 4 | 12 | Advance planning has determined specification of appropriate power supplies and distribution equipment. Equipment to be supplied as thoroughly inspected prior to dispatch from warehouse and safe for use. Electrical services and equipment to be installed by competent contractors. | All cables and electrical equipment to be visually inspected before installation for damage or fault. Circuits to be protected by appropriate MCB/RCD. Generators and distribution to be isolated from or unauthorised access by barriers and warning signage. Cables shall be routed to avoid trip hazards or obstruct gangways and emergency exits and covered by suitable materials in visitors areas. All cabling and distribution will be installed in accordance with BS7909: 2011 Code of practice. All metal-framed structures provided with electrical supplies to be bonded to earth. | Safety Advisor Production Director | As per production schedule | 1 | 3 | 3
16 | Use of Work Equipment and Tools
17 | Injury from misuse, ejection of materials, | Event Staff | 3 | 2 | 6 | Limited requirement for use of power tools. Personnel trained and experienced in use of tools relevant to the task. | Equipment to be visually checked prior to use. All carpentry & metal work to be contained in designated zones away from other workers and areas. Appropriate PPE to be used by personnel. | Safety Advisor | As per production schedule | 1 | 2 | 2
18 | Lighting, Sound and Video Installations
19 | Falling Objects | Event Staff and Visitors | 2 | 4 | 8 | Equipment to be installed as per plan approved by structure contractor or engineer. Motors and lifting equipment to be subject to appropriate formal inspection system. | Equipment installed with secondary safety bonds where appropriate. Installation undertaken and checked by competent personnel from the relevant department. Work zone is a hard hat area. | Safety Advisor Production Director | As Per production schedule | 1 | 4 | 4
20 | Electric Shock or Burns | Event Staff and Visitors | 3 | 3 | 9 | Equipment to be supplied as maintained and in good serviceable condition. Distribution of stage power supplies designed to ensure adequate load capacities are in place. | Circuits to be protected by appropriate MCB/RCD. Equipment visually inspected during installation. Equipment installed by competent personnel only with appropriate experience of stage equipment installations. Installation to be checked by competent electrician to ensure that circuits unlikely to become overloaded. | Safety Advisor Production Director | As Per production schedule | 1 | 3 | 3
21 | Noise | Event Staff | 3 | 3 | 9 | Audio system design to provide coverage to audience areas with minimal dispersion off axis | Hearing protection to be available for all personnel working in areas of high exposure. | Safety Advisor Production Director | As Per production schedule | 1 | 3 | 3
22 | Storage and Stacking
23 | Unauthorized access. | Event Staff and Visitors | 2 | 4 | 8 | Storage areas identified on site plan. | Storage secured from general access by means of fencing or barriers. | Safety Advisor | As Per schedule | 1 | 4 | 4
24 | Unstable Stacks. | Event Staff | 2 | 4 | 8 | Planning to include sufficient storage space for materials. | Stacking to be undertaken by experienced personnel to minimise likelihood of materials becoming unstable. | Safety Advisor | As Per schedule | 1 | 4 | 4
25 | Staff Welfare
26 | General Welfare | Event Staff and Visiting performers | 2 | 2 | 4 | Site accommodation is permanent and purpose built offices, providing a maintained acceptable level of comfort. Sufficient breaks built into the build and break schedule to ensure that all staff get reasonable breaks from the heat during the day | Sufficient air conditioning and water to be available to all staff. Facilities for provision of refreshment to be available and maintained. | Production Director Safety Advisor | As per schedule | 1 | 2 | 2
27 | Hot Environment | All persons On site | 2 | 2 | 4 | Advice to all workers to drink plenty of water, apply sunscreen, use sunglasses and hats. Many of the workers on-site are used to working in this environment. | Provision of sunscreen and drinking water. Provide workers with sufficient breaks and a shaded area in which to rest. Briefing to all workers about the dangers of working in heat and to advise workers to look out for each other to ensure no one gets heat stroke. | Production Director Safety Advisor | Throughout | 1 | 2 | 2
28 | Sanitary Facilities | Staff | 2 | 2 | 4 | Site plan includes appropriate accommodation and toilet/hand wash facilities for all staff and guests. | Toilets to be regularly maintained and cleaned. Suitable and sufficient toilet facilities throughout event. | Operations Manager Safety Advisor | Per schedule | 1 | 2 | 2
29 | Emergency Egress
30 | Adverse Crowd Dynamics leading to Crushing, Trips and Falls | Event Staff and Visitors | 3 | 5 | 15 | Site designed to ensure adequate means of escape for all staff and guests from event site. Perimeter fence and security staff installed to prevent public entering site. Emergency routes to be clearly signed and to receive sufficient lighting under the hours of darkness. | Emergency access and egress routes to be maintained as clear of obstruction at all times. The monitoring of the above control to be managed by appointed security company. Security staff to receive briefing on actions to be taken in the case of an emergency | Production Director Safety Advisor Security Manager | During Event | 1 | 5 | 5
31 | Power failure | Event Staff and Visitors | 1 | 5 | 5 | TDS will have appropriate battery powered emergency lighting installed. Generators set up as redundant twin or triple sets. TDS lighting wired to alternating generators if necessary. | Emergency lighting functionality to be checked before every concert. | Safety Advisor Production Director | During Event | 1 | 3 | 3
32 | Temporary Demountable Structures
33 | Structural Failure leading to Collapse | Event Staff and Visitors | 3 | 5 | 15 | Structures sourced from competent contractor(s). Structures to be designed for anticipated use and confirmed as suitable by competent persons. Anticipated applied loads to be confirmed between structure contractor, production contractors and engineer. Wind and weather management plan to be in place. Wind and weather monitored throughout event period and managed according to plans agreed between the event team and relevant authorities. | Structures confirmed, by a certificate of completion, as built according to approved plans. Applied production loads confirmed as built according to plan. Appropriate ballast or anchoring in place for all relevant structures to prevent uplift, overturning or failure within limits of wind and weather management plan. In the event of high winds, all contractors are required to monitor their own structures for stability, and take such remedial measures as are appropriate to maintain the integrity of the structure (such as closing all doors and flaps on marquees, or removing blow-out panels in stages as appropriate) LED screens and other flown equipment shall be lowered and secured. The ensures that all fencing, towers and other structures to which scrims or branding has been attached are properly secured. If movement occurs, the branding or scrim be removed immediately. | Production Director Safety Advisor | As Per schedule | 1 | 5 | 5
34 | Safety of Visitors Areas
35 | Blocking of Access Routes | Event Staff Visitors | 2 | 2 | 4 | Site defined in plans to include secure perimeter and appropriate access/egress points for projected number of visitors. Projections made on competent feedback and vocational experience from previous events. | Access and egress routes to be maintained as free of obstruction at all times. Security personnel to manage all access and egress points. Perimeter fence to be clad in screening to prevent viewing of event site by non-ticket holders and minimize crowding external to the event site. | Operations Manager Safety Advisor | During Event | 1 | 2 | 2
36 | Bodily injury from car crash | Event Staff and Visitors | 3 | 5 | 15 | Cordoned off viewing areas. Competent licensed drivers. Public not permitted to drive. | Monitoring of drivers behavior. Audience kept clear of driving area | Operations Manager Safety Advisor Security | During Event | 1 | 6 | 6
37 | Damage to Ground | Event Staff Visitors | 3 | 3 | 9 | Work activities planned to prevent damage to roads, pathways leading to trip or fall hazards. Unstable or weak ground areas to be identified in advance and signed or barrier to prevent access by heavy vehicles. | Any work activity leading to or causing ground damage to be reported immediately to Events management Soft ground or areas venerable to damage to be covered/protected with temporary flooring or pathway. | Operations Manager Security | Per schedule | 1 | 2 | 2
38 | Uneven Ground | Event Staff Visitors | 3 | 2 | 6 | All areas within site to be surveyed for defects prior to occupation of the site. Access routes over soft and uneven (pebbled) ground to be covered with temporary ply flooring. Sanded construction area rolled and flattened to provide clear surface area. Note that the nature of the surface will mean that perfect ground conditions cannot be achieved at all times. | Any defective or hazardous areas to be temporarily barriered until remedial work can be undertaken. Access and egress routes to be inspected daily. | Safety Advisor Operations Manager | Per schedule | 1 | 2 | 2
39 | Insufficient Lighting leading to Trip, Fall or Similar Incidents | Visitors | 3 | 3 | 9 | Site planned to include appropriate provision for lighting to all key areas of the site. Existing and permanent lighting will be where zone entrances meet the road. | Tower lights on access roads installed and general temporary lighting installed throughout the site. | Production Director Safety Advisor | Per schedule | 1 | 3 | 3
40 | Visitors Welfare Facilities |  | 3 | 2 | 6 | Site plans to include sufficient visitors sanitary and first aid facilities and refreshment opportunities. Sufficient facilities installed to meet projected needs of visitors. | Signage in place to guide visitors to locations as necessary. Facilities monitored for cleanliness and operation. Steward staff on hand to assist guide visitors to alternative facilities. | Production Director Safety Advisor | As Per schedule | 1 | 2 | 2
41 | First Aid and Emergency Arrangements
41 | Medical incidents during build/derig | Staff | 2 | 5 | 10 | All contractors required to have their own first aid trained personnel and first aid kit at their work place. Staff are made aware of location of first aid kit. Means of communication with emergency services to be in place. Clear routes for emergency vehicles to be kept at all times during the build and de-rig | First aid provisions monitored. First aid kit restocked once used. Staff monitored for signs of fatigue. | Production Director Safety Advisor | Constantly | 1 | 5 | 5
42 | Any Visitors Safety Incident |  | 3 | 5 | 15 | Event safety management plan to detail arrangements for communication of incidents between event management and emergency responders. Advance consultation with civil defence, first aid and medical providers, security contractors and police. Assembly points are established and appropriate signage installed. Additional site lighting will be provided for egress routes. | An Emergency Evacuation Procedure has been developed. This procedure shall be communicated to all staff and security members prior to the event commencing. Pre-scripted announcements shall be used to advise the visitors of what has occurred and the action they need to take to remain safe. All evacuation routes to be manned and kept clear at all time. Suitable audience lighting to be made available and activated to assist with evacuation of areas during periods of darkness. Medical staff to be in place prior to show opening. Facilities, staff and signage in place to assist manage movements of crowds in emergency situation. | Production Director Safety Advisor | During Event | 1 | 5 | 5